## READ ME
DIRECTORY
Name | Nickname | Primary | Lark Email |  | Phone Number
Keoni Dylim | Keoni | john.dylim@student.ateneo.edu | keonidyl@gmail.com |  | 9164470151
Luis Madrid | Luis | luis.c.madrid@student.ateneo.edu | luiscabmadrid@gmail.com |  | 9777004003
Sprint Overview |  |  |  | Sprint Planning
What a Sprint Is A sprint is a fixed, short work cycle (usually 1 week in your case). (Each sprint delivers a usable, testable increment of the system.) How Sprints Fit the Project The overall timeline defines phases and priorities. Each sprint selects a small subset of components/tasks from the backlog. Scope is locked once the sprint starts; (unfinished work rolls into the next sprint.) — What Comes Out of Every Sprint — Completed features or components —Updated sprint document — Feedback for improvement (process + product) |  |  |  | 1. Sprint Planning Meeting When: Weekly sprint meet Agenda a. Review project priorities & timeline b. Define the sprint goal c. Select tasks/components for the sprint d. Assign owners & confirm feasibility e. Finalize sprint document Output - Accepted or revised features - Feedback for next sprint
2. Sprint Review (Demo) When: Weekly sprint meet Agenda Demo completed features Review sprint goal vs actual output Collect feedback Confirm accepted work Output - Accepted or revised features - Feedback for next sprint
3. Stand-Up Meetings When: Daily or 2–3× a week (5–10 mins) Agenda a. What did I complete? b. What will I work on next? c. Any blockers? Output - Updated task status - Blockers identified early

## Directory
MILESTONE TRACKER
Module Name | Soft Deadline | Days Left | Status | Deliverable Link
Development, Env Setup, & Testing | 2026-02-06 | -3 | Done
Core Architecture Module | 2026-02-14 | 5 | Doing
Order Fulfillment Module | 2026-02-28 | 19 | Not Started
Inventory Module | 2026-03-07 | 26 | Not Started
Customer Management Module | 2026-03-14 | 33 | Not Started
Reporting & Analytics Module | 2026-03-21 | 40 | Not Started
SLIDE DECK LINKS
Event Name | Date Presented | Link | Minutes File*
[5Byte x SPM] Jumpstart Dev Alignment | 2026-02-03 | https://www.canva.com/design/DAHAPXrpGws/ho4AtDiaoLu7CXx6K7bywA/edit
[5Byte x SPM] Mastersheet Briefing Alignment | 2026-02-05 | https://www.canva.com/design/DAHAbsBReKc/K7DVozPNN19m-SQVCU_dng/edit
DOCUMENT LINKS
Document Name | Link | Status | Key Contents / Remarks
Petrozone BPMN Assessment | [5Byte x SPM] Client Documentation | Working | Gap Analysis, Current process flows
5Byte Use Case Diagrams | [5Byte x SPM] Client Documentation | Working | Modular Requirements
5Byte User Stories | [5Byte x SPM] Client Documentation | Working
Sprint Documentation/Tracker | [5Byte X SPM] Masterfile | Working
Sprint Documentation/Tracker | [5Byte X SPM] Masterfile | Working
Formulas:
Days Left = DATEVALUE([Soft Deadline])-TODAY()

## Sprints
ID | Sprint | WBS | WBS Task / Module | Components Included (from WBS) | FR No. | Functional Requirement Supported | Component | Resources | Notes | Priority | Developers | Status | Related Use Case | User Stories
1 | Sprint 1 ¦ Feb 1-7 | 1 | Development & Testing | Dev environment setup, testing plan | — | Sprint setup, test strategy definition | Dev Environment Configuration |  | 5BYTE-SCRUM_MTG | HIGH | Frankie Pinat, Lyka Gutierrez | COMPLETED
2 | Sprint 2 ¦ Feb 8 – Feb 14 | 2 | Core Architecture Module | Manage Branch Profiles | FR-9 | Create, update, and link branch profiles to users, customers, vehicles | Vehicle Profile UI |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Completed | UC1,UC2,UC3,UC4 | US1,US2,US3,US4
3 | Sprint 2 ¦ Feb 8 – Feb 14 |  |  | Manage User Roles | FR-7 | Role-based access control, role templates, branch assignment | Vehicle Data Model |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Completed | UC10, UC11, UC12, UC13 | US10, US11, US12, US13
4 | Sprint 2 ¦ Feb 8 – Feb 14 |  |  | Enforce User Log-in | FR-8 | Secure authentication, admin-only user creation | Services & Products UI |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Completed | UC5,UC6, UC7, UC8 | US5,US6, US7, US8
5 | Sprint 2 ¦ Feb 8 – Feb 14 |  |  | Enforce Mandatory Fields | FR-12 | Validation rules on critical forms | Services–Products Mapping |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Completed | UC14, UC15, UC16, UC17 | US14, US15, US16, US17
6 | Sprint 2 ¦ Feb 8 – Feb 14 |  |  | Record Audit Logs | FR-17 | System-wide audit trail for all key actions | Job Order Workflow Engine |  |  | LOW | Frankie Pinat, Lyka Gutierrez | In Progress | UC18 | US18
7 | Sprint 2 ¦ Feb 8 – Feb 14 |  |  | Core Architecture Module Testing | — | Verification of RBAC, login, branch logic | Job Order UI |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
8 |  | 3 | Order Fulfillment Module | Manage Vehicle Profiles | FR-1 | Vehicle CRUD, OR/CR storage, service history | Inventory Auto-Deduction |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
9 |  |  |  | Manage Services, Products, Packages | FR-2 | Many-to-many service–product–package management | Operational Dashboard UI |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
10 |  |  |  | Manage Pricing Matrices | FR-10 | Labor and pricing tables used for quotations | Dashboard Data Services |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Not started
11 |  |  |  | Generate Job Orders | FR-3 | End-to-end job order workflow with templates | Report Configuration UI |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
12 |  |  |  | Manage Customer Profiles | FR-15 | Customer CRUD, vehicle and service linkage | Report Export Engine |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Not started
13 |  |  |  | Record Third-Party Repairs | FR-16 | Open-ended repair records outside menus | Purchase Order Management |  |  | LOW | Frankie Pinat, Lyka Gutierrez | Not started
14 |  |  |  | Order Fulfillment Module Testing | — | Validation of job order lifecycle & pricing | RBAC Engine |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
15 |  | 4 | Inventory Module | Record Stock-In | FR-6 | Purchase orders, stock replenishment templates | Role-Based UI Adaptation |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
16 |  |  |  | Manage Supplier Profiles | FR-13 | Supplier CRUD with contact and linkage | Authentication Module |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Not started
17 |  |  |  | Manage Supplier Products | FR-14 | Supplier–product one-to-one mapping | Branch Management UI |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Not started
18 |  |  |  | Inventory Module Testing | — | Inventory accuracy and PO logic testing | Pricing Matrix Engine |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
19 |  | 5 | Customer Management Module | Send Service Reminders | FR-19 | Automated service reminders via SMS/Email | Performance Analytics Engine |  |  | LOW | Frankie Pinat, Lyka Gutierrez | Not started
20 |  |  |  | Push System Notifications | FR-18 | Job status alerts to relevant users | Validation Layer |  |  | LOW | Frankie Pinat, Lyka Gutierrez | Not started
21 |  |  |  | Customer Management Module Testing | — | Notification and reminder verification | Supplier Profile UI |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
22 |  | 6 | Reporting & Analytics Module | Real-Time Dashboards | FR-4 | Live sales, inventory, and workshop metrics | Supplier Product Mapping |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
23 |  |  |  | Generate Reports | FR-5 | Configurable and exportable reports | Customer Profile UI |  |  | HIGH | Frankie Pinat, Lyka Gutierrez | Not started
24 |  |  |  | Display Staff Performance Analytics | FR-11 | Job completion time, sales per staff | Third-Party Repair Records |  |  | MEDIUM | Frankie Pinat, Lyka Gutierrez | Not started
25 |  |  |  | Reporting & Analytics Module Testing | — | Data accuracy and performance validation | Audit Logging Service |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
26 |  | 7 | Slack Time | Bug fixing, refinements | All | Cross-module stabilization | Notification Engine |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
27 |  | 8 | Sprints Documentation | Sprint & system documentation | All | Technical and user documentation | Reminder Scheduler |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started
28 |  | 9 | System Prototype Approval | Final review & sign-off | All | Client acceptance of prototype | Core Architecture |  |  |  | Frankie Pinat, Lyka Gutierrez | Not started

## UCUS
Feature/ Theme | UC | Persona | Functionality | US | STORY | ACCEPTANCE CRITERIA | FR/NFR
Core Architecture | UC1 | HM, POC, JS, R | Create Branch Profile | US1 | As a HM, POC, JS, or R, I want to create a branch profile so the branch can be registered in the system. | Branch profile is saved within ≤3 seconds, with 100% mandatory field validation enforced | FR-9
| UC2 | HM, POC, JS, R | View Branch Profille | US2 | As a HM, POC, JS, or R, I want to view branch profile details for reference and management | Branch details load within ≤2 seconds with 100% data accuracy | FR-9
| UC3 | HM, POC, JS, R | Update Branch Profille | US3 | As a HM, POC, JS, or R, I want to update branch profile information to keep records current | Updates are saved successfully in ≥99% of valid submissions and reflected immediately. | FR-9
| UC4 | HM, POC, JS, R | Delete Branch Profille | US4 | As a HM, POC, JS, or R, I want to delete a branch profile to remove inactive branches | Branch profile is removed from active selection in 100% of deletion attempts | FR-9
| UC5 | HM, POC, JS, R, T | Log into system | US5 | As a HM, POC, JS, R, or T, I want to log into the system to access my assigned features | Login succeeds for valid credentials in ≥99% of attempts with response time ≤2 seconds | FR-8
| UC6 | HM, POC, JS, R, T | Log out of system | US6 | As a HM, POC, JS, R, or T, I want to log out to securely end my session | Session is terminated immediately and access is revoked in 100% of logout actions | FR-8
| UC7 | HM, POC, JS, R, T | View Account | US7 | As a HM, POC, JS, R, or T, I want to view my account details for verification | Account information loads within ≤2 seconds with 100% role-based access enforcement | FR-7
| UC8 | HM, POC, JS, R, T | Forgot Password | US8 | As a HM, POC, JS, R, or T, I want to reset my password if I forget it | Password reset is completed successfully in ≥95% of requests within ≤5 minutes | FR-8
| UC9 | HM, POC, JS, R, T | Change Password | US9 | As a HM, POC, JS, R, or T, I want to change my password to maintain account security | New password meets 100% complexity rules and is enforced on next login | FR-8
| UC10 | HM, POC, JS | Create user accounts | US10 | As a HM, POC, or JS, I want to create user accounts to grant system access | User accounts are created successfully in ≥98% of valid submissions with correct role and branch assignment | FR-7
| UC11 | HM, POC, JS | View user accounts | US11 | As a HM, POC, or JS, I want to view user accounts for oversight and management | User list loads within ≤3 seconds with 100% accurate role and status data | FR-7
| UC12 | HM, POC, JS | Update user accounts | US12 | As a HM, POC, or JS, I want to update user account details to reflect role or status changes | Changes are applied and enforced in ≤1 minute in ≥99% of cases | FR-7
| UC13 | HM, POC, JS | Delete user accounts | US13 | As a HM, POC, or JS, I want to delete user accounts to revoke access | Deleted accounts are prevented from logging in in 100% of cases | FR-7
| UC14 | HM, POC, JS | Create Mandatory Fields | US14 | As a HM, POC, or JS, I want to define mandatory fields to enforce data completeness | Deleted accounts are prevented from logging in in 100% of cases | FR-12
| UC15 | HM, POC, JS | View Mandatory Fields | US15 | As a HM, POC, or JS, I want to view mandatory field configurations for validation reference | Configuration list loads within ≤2 seconds with 100% accuracy | FR-12
| UC16 | HM, POC, JS | Update Mandatory Fields | US16 | As a HM, POC, or JS, I want to update mandatory field rules to match business needs | Updated rules take effect in ≤5 minutes for 100% of new records. | FR-12
| UC17 | HM, POC, JS | Delete Mandatory Fields | US17 | As a HM, POC, or JS, I want to remove mandatory field rules that are no longer required | Deleted rules are no longer enforced in 100% of subsequent transactions | FR-12
| UC18 | HM, POC | Record Audit Log | US18 | As a HM or POC, I want system actions to be logged for traceability and compliance | 100% of critical actions generate audit logs with user ID, timestamp, and action typ | FR-17
Inventory | UC19 | HM, POC, JS, R | Create purchase orders for inventory | US19 | As an HM, POC, JS, or R, I want to create a purchase order so inventory items can be procured. | Purchase order is saved within ≤3 seconds with 100% mandatory field validation enforced. | FR-6
| UC20 | HM, POC, JS, R | View purchase orders for inventory | US20 | As an HM, POC, JS, or R, I want to view purchase orders for tracking and reference. | Purchase order details load within ≤2 seconds with 100% data accuracy. | FR-6
| UC21 | HM, POC, JS, R | Update purchase orders for inventory | US21 | As an HM, POC, JS, or R, I want to update purchase orders to keep inventory records current. | Updates are saved successfully in ≥99% of valid submissions and reflected immediately. | FR-6
| UC22 | HM, POC, JS, R | Delete purchase orders for inventory | US22 | As an HM, POC, JS, or R, I want to delete purchase orders to remove invalid or cancelled entries. | Deleted purchase orders are removed from active records in 100% of deletion attempts. | FR-6
| UC23 | HM, POC, JS, R | Create labor and packaging pricing matrices | US23 | As an HM, POC, JS, or R, I want to create labor and packaging pricing matrices to define standardized costs. | Pricing matrix is saved within ≤3 seconds with complete validation of required fields. | FR-6
| UC24 | HM, POC, JS, R, T | View labor and packaging pricing matrices | US24 | As an HM, POC, JS, R, or T, I want to view labor and packaging pricing matrices for cost reference. | Pricing matrix data loads within ≤2 seconds with 100% accuracy. | FR-6
| UC25 | HM, POC, JS, R | Update labor and packaging pricing matrices | US25 | As an HM, POC, JS, or R, I want to update pricing matrices to reflect cost changes. | Updates are successfully saved in ≥99% of valid submissions and applied immediately. | FR-6
| UC26 | HM, POC, JS, R | Delete labor and packaging pricing matrices | US26 | As an HM, POC, JS, or R, I want to delete pricing matrices that are no longer applicable. | Pricing matrix is removed from active selection in 100% of deletion attempts. | FR-6
| UC27 | HM, POC, JS | Create Supplier Profile | US27 | As an HM, POC, or JS, I want to create a supplier profile to register suppliers in the system. | Supplier profile is saved within ≤3 seconds with 100% mandatory field validation. | FR-13
| UC28 | HM, POC, JS | View Supplier Profile | US28 | As an HM, POC, or JS, I want to view supplier profiles for reference and management. | Supplier profile details load within ≤2 seconds with 100% data accuracy. | FR-13
| UC29 | HM, POC, JS | Edit Supplier Profile | US29 | As an HM, POC, or JS, I want to edit supplier profiles to keep supplier information updated. | Supplier profile updates are saved successfully in ≥99% of valid submissions. | FR-13
| UC30 | HM, POC, JS | Delete Supplier Profile | US30 | As an HM, POC, or JS, I want to delete supplier profiles to remove inactive suppliers. | Supplier profile is removed from active records in 100% of deletion attempts. | FR-13
| UC31 | HM, POC, JS | Create Supplier Product | US31 | As an HM, POC, or JS, I want to create supplier products to link items with suppliers. | Supplier product is created within ≤3 seconds with full validation of required fields. | FR-14
| UC32 | HM, POC, JS | View Supplier Product | US32 | As an HM, POC, or JS, I want to view supplier products for inventory reference. | Supplier product details load within ≤2 seconds with 100% accuracy. | FR-14
| UC33 | HM, POC, JS | Edit Supplier Product | US33 | As an HM, POC, or JS, I want to edit supplier products to reflect pricing or item changes. | Supplier product updates are saved successfully in ≥99% of valid submissions. | FR-14
| UC34 | HM, POC, JS | Delete Supplier Product | US34 | As an HM, POC, or JS, I want to delete supplier products that are no longer offered. | Supplier product is removed from active records in 100% of deletion attempts. | FR-14
Order Fulfillment | UC35 | POC, JS, R | Create quotations | US35 | As a POC, JS, or R, I want to create quotations to formally propose service costs to customers | Quotation is created within ≤5 seconds with 100% mandatory fields completed and ≥95% pricing accuracy
| UC36 | HM, POC, JS, R, T | View quotations | US36 | As a HM, POC, JS, R, or T, I want to view quotations for tracking and reference | Quotation details load within ≤3 seconds with 100% data accuracy
| UC37 | POC, JS, R, T | Update quotations | US37 | As a POC, JS, R, or T, I want to update quotations to reflect changes in scope or pricing | Updates are saved successfully in ≥98% of valid edits and reflected immediately
| UC38 | POC, JS, R | Delete quotations | US38 | As a POC, JS, or R, I want to delete quotations that are no longer needed | Deleted quotations are removed from active records in 100% of cases.
| UC39 | POC, JS, R, T | Create job estimates | US39 | As a POC, JS, R, or T, I want to create job estimates to plan service execution | Job estimate is created within ≤5 seconds using validated labor and parts data in ≥95% of transactions
| UC40 | HM, POC, JS, R, T | View job estimates | US40 | As a HM, POC, JS, R, or T, I want to view job estimates for approval and monitoring | Job estimate details load within ≤3 seconds with 100% accuracy
| UC41 | POC, JS, R, T | Update job estimates | US41 | As a POC, JS, R, or T, I want to update job estimates when service details change | Updates are applied in ≤1 minute for ≥98% of valid updates
| UC42 | POC, JS, R | Delete job estimates | US42 | As a POC, JS, or R, I want to delete invalid or canceled job estimates | Deleted estimates cannot be converted into job orders in 100% of cases
| UC43 | POC, JS, R | Create order cards | US43 | As a POC, JS, or R, I want to create order cards to track active service work | Order card is created successfully in ≤5 seconds and linked to a valid job estimate 100% of the time
| UC44 | HM, POC, JS, R, T | View order cards | US44 | s a HM, POC, JS, R, or T, I want to view order cards to monitor service progress. | Order card details load within ≤3 seconds with real-time status visibility
| UC45 | POC, JS, R, T | Update order cards | US45 | As a POC, JS, R, or T, I want to update order cards as work progresses | Status updates are saved in ≥99% of valid submissions and visible in real time
| UC46 | POC, JS, R | Delete order cards | US46 | As a POC, JS, or R, I want to delete order cards for canceled jobs | Deleted order cards are removed from active workflow in 100% of cases
| UC47 | R, T | Ask for customer approval | US47 | As a R or T, I want to request customer approval to proceed with service work | Approval request is sent successfully in ≥95% of attempts with complete service details
| UC48 | R, T | Receive customer approval | US48 | As a R or T, I want to record customer approval to proceed with the job | Approval status is updated in ≤2 minutes and logged in 100% of approved transactions
| UC49 | HM, POC, JS, R, T | Add Third Party Repair | US49 | As a HM, POC, JS, R, or T, I want to add third-party repair details for outsourced services | Third-party repair record is saved with 100% required fields completed
| UC50 | HM, POC, JS, R, T | View Third Party Repair | US50 | As a HM, POC, JS, R, or T, I want to view third-party repair information for tracking | Records load within ≤3 seconds with 100% data accuracy
| UC51 | HM, POC, JS, R, T | Update Third Party Repair | US51 | As a HM, POC, JS, R, or T, I want to update third-party repair details as needed | Updates are reflected in ≥98% of valid edits within ≤1 minute
| UC52 | HM, POC, JS, R, T | Delete Third Party Repair | US52 | As a HM, POC, JS, R, or T, I want to delete third-party repair records when no longer applicable | Deleted records are excluded from billing and reports in 100% of cases
Customer Management | UC53 | HM, POC, JS, R, T | View Customer database | US53 | As an HM, POC, JS, R, or T, I want to view the customer database to access customer information for reference and management. | Customer records load within ≤2 seconds with 100% data accuracy and role-based access enforced.
| UC54 | POC, JS, R, T | Update Customer database | US54 | As a POC, JS, R, or T, I want to update customer records to keep customer information current. | Customer updates are saved successfully in ≥99% of valid submissions and reflected immediately.
| UC55 | POC, JS, R | Delete Customer database | US55 | As a POC, JS, or R, I want to delete customer records to remove inactive or invalid entries. | Customer records are removed from active records in 100% of deletion attempts.
| UC56 | HM, POC, JS | Create system notifications | US56 | As an HM, POC, or JS, I want to create system notifications to communicate important updates to users. | System notification is created within ≤3 seconds with complete validation of required fields. | FR-19
| UC57 | HM, POC, JS, R, T | Receive system notifications | US57 | As an HM, POC, JS, R, or T, I want to receive system notifications to stay informed of relevant updates. | Notifications are delivered to intended recipients in ≥99% of cases within acceptable response time. | FR-19
| UC58 | HM, POC, JS | Update system notifications | US58 | As an HM, POC, or JS, I want to update system notifications to revise message content or settings. | Notification updates are saved successfully in ≥99% of valid submissions and applied immediately. | FR-19
| UC59 | HM, POC, JS | Delete system notifications | US59 | As an HM, POC, or JS, I want to delete system notifications that are no longer needed. | Deleted notifications are removed from active notifications in 100% of deletion attempts. | FR-19
| UC60 | POC, JS, R | Create Service Reminder Delivery | US60 | As a POC, JS, or R, I want to create service reminder deliveries to notify customers of upcoming services. | Service reminder delivery is created within ≤3 seconds with 100% mandatory field validation. | FR-18
| UC61 | POC, JS, R | View Service Reminder Delivery | US61 | As a POC, JS, or R, I want to view service reminder deliveries to monitor reminder status. | Service reminder delivery details load within ≤2 seconds with 100% accuracy. | FR-18
| UC62 | POC, JS, R | Update Service Reminder Delivery | US62 | As a POC, JS, or R, I want to update service reminder deliveries to adjust schedules or content. | Updates are saved successfully in ≥99% of valid submissions and reflected immediately. | FR-18
| UC63 | POC, JS, R | Delete Service Reminder Delivery | US63 | As a POC, JS, or R, I want to delete service reminder deliveries that are no longer required. | Service reminder deliveries are removed from active records in 100% of deletion attempts. | FR-18
| UC64 | POC, JS, R | Send Service Reminder Delivery | US64 | As a POC, JS, or R, I want to send service reminder deliveries to ensure customers are notified on time. | Service reminders are sent successfully to intended recipients in ≥99% of delivery attempts. | FR-18
Reporting and Analytics | UC65 | HM, POC, JS, R | View Real-time dashboards | US65 | As a HM, POC, JS, or R, I want to view real-time dashboards to monitor sales, inventory, and operations | Dashboards load within ≤5 seconds and reflect data updated within the last ≤5 minutes with ≥98% accuracy
| UC66 | HM, POC, JS, R | Filter real-time dashboards | US66 | As a HM, POC, JS, or R, I want to filter dashboards by branch, date, or category for focused analysis | Applied filters update dashboard views in ≤3 seconds and return correct results in ≥98% of cases
| UC67 | HM, POC, JS | Create staff performance analytics | US67 | As a HM, POC, or JS, I want to create staff performance analytics to evaluate productivity and efficiency | Analytics configuration is saved successfully in ≥95% of valid submissions and applied to staff data
| UC68 | HM, POC, JS, R, T | View staff performance analytics | US68 | As a HM, POC, JS, R, or T, I want to view staff performance analytics for monitoring and decision-making | Analytics reports load within ≤4 seconds with 100% role-based access enforcement
| UC69 | HM, POC, JS | Update staff performance analytics | US69 | As a HM, POC, or JS, I want to update staff performance analytics to reflect new KPIs or thresholds | Updates take effect in ≤5 minutes for 100% of new analytics calculations
| UC70 | HM, POC, JS | Delete staff performance analytics | US70 | As a HM, POC, or JS, I want to delete staff performance analytics that are no longer relevant | Deleted analytics are excluded from dashboards and reports in 100% of cases
| UC71 | HM, POC, JS, R | Create customizable reports | US71 | As a HM, POC, JS, or R, I want to create customizable reports for flexible reporting needs | Reports are generated successfully in ≥95% of valid configurations using selected filters and fields
| UC72 | HM, POC, JS, R | Export customizable reports | US72 | As a HM, POC, JS, or R, I want to view customizable reports for analysis and review | Reports load within ≤5 seconds with 100% data accuracy
| UC73 | HM, POC, JS, R | View customizable reports | US73 | As a HM, POC, JS, or R, I want to export reports for external reporting and sharing | Reports export successfully in ≥98% of attempts within ≤10 seconds in supported formats (e.g., PDF, CSV)
| UC74 | HM, POC, JS, R | Delete customizable reports | US74 | As a HM, POC, JS, or R, I want to delete customizable reports that are no longer needed | Deleted reports are permanently removed and inaccessible in 100% of cases

## Test Case Inventory
Test Case Inventory
MODULE | TEST TYPE | START | END | TOTAL TEST | TOTAL DEFECTS | STATUS | TEST OWNER | REMARKS
Core Architecture | Unit, Security, Performance, Configuration | 2026-02-11 | 2026-02-12 | 10 | 0
Order Fulfillment | Functional, Validation, Workflow, Negative | 2026-02-18 | 2026-02-19 | 0 | 0
Inventory | Functional, Data Integrity, Boundary, Concurrency, Regression | 2026-02-25 | 2026-02-26 | 0 | 0
Customer Management | Functional, Usability, Performance, Data Integrity | 2026-03-04 | 2026-03-05 | 0 | 0
Reporting & Analytics | Functional, Data Integrity, Real-Time, RBAC, Performance | 2026-03-11 | 2026-03-12 | 0 | 0
Integration & Final UAT | E2E, Cross-Module Data Flow, UAT, Regression, Deployment Readiness | 2026-03-16 | 2026-03-17 | 0 | 0

## 01-Core Architecture
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Core Architecture Module |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 10
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-02-11 | 2026-02-12
TEST OBJECTIVES Brief description of the testing goals
The objective of testing the Core Architecture Module is to verify that Petrozone Pulse’s foundational system components are stable, secure, and enforce standardized system rules across all branches. Testing will ensure that user authentication, role-based access control, branch management, and mandatory field validation function correctly and consistently. Specifically, testing aims to confirm that: Login and authentication mechanisms correctly validate users, enforce session and lockout rules, and prevent unauthorized access. Role-based access control (RBAC) reliably restricts system features and APIs based on assigned user roles and branch associations. Core system validations—including mandatory fields, configuration parameters, and data integrity rules—are consistently enforced across all core APIs. Audit logging accurately records critical system actions and changes, providing traceability and compliance for operational transparency. Core services and APIs initialize correctly, remain available under expected usage, and provide a stable foundation for dependent modules. Successful completion of these tests will demonstrate that the Core Architecture Module meets approved requirements and is ready to support higher-level functional, integration, and user acceptance testing.
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 10 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
CA-01 |  | Security | User Authentication Validation Verify that only valid credentials allow system access. | 1. Enter valid username and password 2. Attempt login | - User successfully authenticated and redirected to assigned homepage - Invalid credentials are rejected with an error message
CA-02 |  | Security | Role-Based Access Control Enforcement Ensure users can only access features permitted by their role | 1. Login as Receptionist 2. Attempt to access to sample module | - Access is denied - System displays "Insufficient permissions" message
CA-03 |  | Security | Session Timeout Handling Verify automatic logout after inactivity period | 1. Login to the system 2. Remain idle for configured timeout duration | - User session expires - User is redirected to login screen
CA-04 |  | Performance | Concurrent User Load Handling Ensure system remains stable under expected concurrent users | 1. Simulate 50 concurrent logins 2. Perform basic navigation and transactions | - No system crashes - Response time degradation ≤ 20%
CA-05 |  | Configuration | Configuration of Mandatory Fields Validate enforcement of required fields across modules | 1. Attempt to save job order without required fields | - System prevents saving - Mandatory fields are highlighted
CA-06 |  | Configuration | Environment Configuration Validation Verify correct setup across environments (Dev, Test, Prod) | 1. Deploy system to test environments 2. Verify database, API endpoints, and logging | - System conncects to correct environment resources - No cross-environment data leakage
CA-07 |  | Configuration | Error Logging and Monitoring Ensure system errors are logged correctly | 1. Trigger a controlled system error 2. Check application logs | - Error is logged with timestamp, user ID and module name
CA-08 |  | Unit | User Role Assignment Logic Validate that the system assigns the correct role upon user creation or update | 1. Create a user with role = “Technician” 2. Retrieve user role from the system | - User role is saved and returned exactly as assigned - No default or unintended role is applied
CA-09 |  | Unit | Password Hashing Verification Validate that passwords are not stored in plain text | 1. Create user with password 2. Inspect stored password value | - Stored value is hashed - Plain text password is never persisted
CA-10 |  | Unit | Login Attempt Lockout Logic Verify that repeated failed login attempts trigger account lockout | 1. Submit incorrect password for the same user account multiple times (5 attempts) 2. Attempt login again with correct credentials | - Account is temporarily locked after the configured number of failed attempts - System blocks login even with correct credentials until lockout period expires
Defect
Density
Defect
Distribution
Test Execution Status

## 02-Order Fulfillment
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Order Fulfillment Module |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-02-18 | 2026-02-19
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 0 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
Defect
Density
Defect
Distribution
Test Execution Status

## 03-Inventory
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Inventory Module |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-02-25 | 2026-02-26
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 0 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
Defect
Density
Defect
Distribution
Test Execution Status

## 04-Customer Management
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Customer Management Module |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-03-04 | 2026-03-05
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 0 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
Defect
Density
Defect
Distribution
Test Execution Status

## 05-Reporting & Analytics
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Reporting & Analytics Module |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-03-11 | 2026-03-12
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 0 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
Defect
Density
Defect
Distribution
Test Execution Status

## Integration & Final UAT
[Sprint Week] Test Summary Report
TITLE |  |  |  |  | TOTAL DEFECTS
Integration & Final UAT |  |  |  |  | 0
PROJECT NAME |  |  |  |  | TOTAL TESTS
Petrozone Pulse |  |  |  |  | 0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mauie De Guzman |  |  | 2026-03-11 | 2026-03-05
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  |  | TEST EXECUTION SUMMARY |  |  | CRITICALITY SUMMARY
TOTAL No. of DEFECTS | 0 |  |  | TOTAL No. of TESTS | 0 |  | Low | 0
Open | 0 |  |  | PASSED | 0 |  | Medium | 0
In Progress | 0 |  |  | FAILED | 0 |  | High | 0
Closed | 0 |  |  | Blocked | 0
Minor | 0 |  |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | TEST TYPE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | CRITICALITY | TESTED BY | REMARKS
Defect
Density
Defect
Distribution
Test Execution Status

## EXAMPLE - Agile Test Report (hidden)
Agile Test Summary Report Template – Example
User to enter Defect Tracking and Text Execution information in the data tables below. Dashboard data, charts, and graphs will populate automatically.
TITLE |  |  |  | TOTAL DEFECTS
EV Charging System Testing Report |  |  |  | 25
PROJECT NAME |  |  |  | TOTAL TESTS
Positive Charge EV Charging System |  |  |  | 150
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mateus Tobin |  | 07/15/20XX | 06/01/20XX | 07/14/20XX
TEST OBJECTIVES Brief description of the testing goals
Ensure the EV charging system operates reliably and efficiently, verify user interface functionality, initiate charging session, and ensure backend data processing.
KEY FINDINGS Summary of major issues and observations
– There are some issues with charging session initiation. – Some users experience login failures.
RECOMMENDATIONS Suggestions for improvement
– Investigate and resolve the charging session initiation issue. – Enhance the user authentication process.
CONCLUSION Overall assessment and next steps
Overall, the system performs well, and critical issues have been identified for resolution. Next steps include addressing the defects and re–testing.
Dashboard Data
DEFECT SUMMARY |  |  | TEST EXECUTION SUMMARY
TOTAL No. of DEFECTS | 25 |  | TOTAL No. of TESTS | 150
Open | 4 |  | PASSED | 109
In Progress | 5 |  | FAILED | 21
Closed | 16 |  | Blocked | 15
Minor | 13 |  | Not Executed | 5
Major | 7
Critical | 5
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
DEF001 | 00/00/0000 |  |  |  | Closed | Minor
DEF002 | 00/00/0000 |  |  |  | In Progress | Major
DEF003 | 00/00/0000 |  |  |  | Open | Critical
DEF004 | 00/00/0000 |  |  |  | In Progress | Critical
DEF005 | 00/00/0000 |  |  |  | Closed | Critical
DEF006 | 00/00/0000 |  |  |  | Closed | Critical
DEF007 | 00/00/0000 |  |  |  | Closed | Critical
DEF008 | 00/00/0000 |  |  |  | Open | Minor
DEF009 | 00/00/0000 |  |  |  | Closed | Minor
DEF010 | 00/00/0000 |  |  |  | Closed | Minor
DEF011 | 00/00/0000 |  |  |  | In Progress | Minor
DEF012 | 00/00/0000 |  |  |  | In Progress | Minor
DEF013 | 00/00/0000 |  |  |  | In Progress | Minor
DEF014 | 00/00/0000 |  |  |  | Open | Minor
DEF015 | 00/00/0000 |  |  |  | Open | Minor
DEF016 | 00/00/0000 |  |  |  | Closed | Minor
DEF017 | 00/00/0000 |  |  |  | Closed | Minor
DEF018 | 00/00/0000 |  |  |  | Closed | Minor
DEF019 | 00/00/0000 |  |  |  | Closed | Minor
DEF020 | 00/00/0000 |  |  |  | Closed | Major
DEF021 | 00/00/0000 |  |  |  | Closed | Major
DEF022 | 00/00/0000 |  |  |  | Closed | Major
DEF023 | 00/00/0000 |  |  |  | Closed | Major
DEF024 | 00/00/0000 |  |  |  | Closed | Major
DEF025 | 00/00/0000 |  |  |  | Closed | Major
Test Execution Data
Test Case ID | DATE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | TESTED BY | REMARKS
TC001 | 00/00/0000 | Verify user login functionality. |  |  |  | PASSED |  | None
TC002 | 00/00/0000 | Verify initiation of charging session. |  |  |  | FAILED |  | Charging session does not start for some users.
TC003 | 00/00/0000 |  |  |  |  | Blocked
TC004 | 00/00/0000 |  |  |  |  | Not Executed
TC005 | 00/00/0000 |  |  |  |  | PASSED
TC006 | 00/00/0000 |  |  |  |  | PASSED
TC007 | 00/00/0000 |  |  |  |  | PASSED
TC008 | 00/00/0000 |  |  |  |  | PASSED
TC009 | 00/00/0000 |  |  |  |  | PASSED
TC010 | 00/00/0000 |  |  |  |  | PASSED
TC011 | 00/00/0000 |  |  |  |  | PASSED
TC012 | 00/00/0000 |  |  |  |  | FAILED
TC013 | 00/00/0000 |  |  |  |  | FAILED
TC014 | 00/00/0000 |  |  |  |  | FAILED
TC015 | 00/00/0000 |  |  |  |  | FAILED
TC016 | 00/00/0000 |  |  |  |  | FAILED
TC017 | 00/00/0000 |  |  |  |  | FAILED
TC018 | 00/00/0000 |  |  |  |  | FAILED
TC019 | 00/00/0000 |  |  |  |  | FAILED
TC020 | 00/00/0000 |  |  |  |  | FAILED
TC021 | 00/00/0000 |  |  |  |  | FAILED
TC022 | 00/00/0000 |  |  |  |  | FAILED
TC023 | 00/00/0000 |  |  |  |  | FAILED
TC024 | 00/00/0000 |  |  |  |  | Blocked
TC025 | 00/00/0000 |  |  |  |  | Blocked
TC026 | 00/00/0000 |  |  |  |  | Blocked
TC027 | 00/00/0000 |  |  |  |  | Blocked
TC028 | 00/00/0000 |  |  |  |  | Blocked
TC029 | 00/00/0000 |  |  |  |  | Blocked
TC030 | 00/00/0000 |  |  |  |  | Blocked
TC031 | 00/00/0000 |  |  |  |  | Blocked
TC032 | 00/00/0000 |  |  |  |  | Blocked
TC033 | 00/00/0000 |  |  |  |  | Blocked
TC034 | 00/00/0000 |  |  |  |  | Blocked
TC035 | 00/00/0000 |  |  |  |  | Blocked
TC036 | 00/00/0000 |  |  |  |  | Blocked
TC037 | 00/00/0000 |  |  |  |  | Blocked
TC038 | 00/00/0000 |  |  |  |  | Not Executed
TC039 | 00/00/0000 |  |  |  |  | Not Executed
TC040 | 00/00/0000 |  |  |  |  | Not Executed
TC041 | 00/00/0000 |  |  |  |  | Not Executed
TC042 | 00/00/0000 |  |  |  |  | FAILED
TC043 | 00/00/0000 |  |  |  |  | FAILED
TC044 | 00/00/0000 |  |  |  |  | FAILED
TC045 | 00/00/0000 |  |  |  |  | FAILED
TC046 | 00/00/0000 |  |  |  |  | FAILED
TC047 | 00/00/0000 |  |  |  |  | FAILED
TC048 | 00/00/0000 |  |  |  |  | FAILED
TC049 | 00/00/0000 |  |  |  |  | FAILED
TC050 | 00/00/0000 |  |  |  |  | PASSED
TC051 | 00/00/0000 |  |  |  |  | PASSED
TC052 | 00/00/0000 |  |  |  |  | PASSED
TC053 | 00/00/0000 |  |  |  |  | PASSED
TC054 | 00/00/0000 |  |  |  |  | PASSED
TC055 | 00/00/0000 |  |  |  |  | PASSED
TC056 | 00/00/0000 |  |  |  |  | PASSED
TC057 | 00/00/0000 |  |  |  |  | PASSED
TC058 | 00/00/0000 |  |  |  |  | PASSED
TC059 | 00/00/0000 |  |  |  |  | PASSED
TC060 | 00/00/0000 |  |  |  |  | PASSED
TC061 | 00/00/0000 |  |  |  |  | PASSED
TC062 | 00/00/0000 |  |  |  |  | PASSED
TC063 | 00/00/0000 |  |  |  |  | PASSED
TC064 | 00/00/0000 |  |  |  |  | PASSED
TC065 | 00/00/0000 |  |  |  |  | PASSED
TC066 | 00/00/0000 |  |  |  |  | PASSED
TC067 | 00/00/0000 |  |  |  |  | PASSED
TC068 | 00/00/0000 |  |  |  |  | PASSED
TC069 | 00/00/0000 |  |  |  |  | PASSED
TC070 | 00/00/0000 |  |  |  |  | PASSED
TC071 | 00/00/0000 |  |  |  |  | PASSED
TC072 | 00/00/0000 |  |  |  |  | PASSED
TC073 | 00/00/0000 |  |  |  |  | PASSED
TC074 | 00/00/0000 |  |  |  |  | PASSED
TC075 | 00/00/0000 |  |  |  |  | PASSED
TC076 | 00/00/0000 |  |  |  |  | PASSED
TC077 | 00/00/0000 |  |  |  |  | PASSED
TC078 | 00/00/0000 |  |  |  |  | PASSED
TC079 | 00/00/0000 |  |  |  |  | PASSED
TC080 | 00/00/0000 |  |  |  |  | PASSED
TC081 | 00/00/0000 |  |  |  |  | PASSED
TC082 | 00/00/0000 |  |  |  |  | PASSED
TC083 | 00/00/0000 |  |  |  |  | PASSED
TC084 | 00/00/0000 |  |  |  |  | PASSED
TC085 | 00/00/0000 |  |  |  |  | PASSED
TC086 | 00/00/0000 |  |  |  |  | PASSED
TC087 | 00/00/0000 |  |  |  |  | PASSED
TC088 | 00/00/0000 |  |  |  |  | PASSED
TC089 | 00/00/0000 |  |  |  |  | PASSED
TC090 | 00/00/0000 |  |  |  |  | PASSED
TC091 | 00/00/0000 |  |  |  |  | PASSED
TC092 | 00/00/0000 |  |  |  |  | PASSED
TC093 | 00/00/0000 |  |  |  |  | PASSED
TC094 | 00/00/0000 |  |  |  |  | PASSED
TC095 | 00/00/0000 |  |  |  |  | PASSED
TC096 | 00/00/0000 |  |  |  |  | PASSED
TC097 | 00/00/0000 |  |  |  |  | PASSED
TC098 | 00/00/0000 |  |  |  |  | PASSED
TC099 | 00/00/0000 |  |  |  |  | PASSED
TC100 | 00/00/0000 |  |  |  |  | PASSED
TC101 | 00/00/0000 |  |  |  |  | PASSED
TC102 | 00/00/0000 |  |  |  |  | PASSED
TC103 | 00/00/0000 |  |  |  |  | PASSED
TC104 | 00/00/0000 |  |  |  |  | PASSED
TC105 | 00/00/0000 |  |  |  |  | PASSED
TC106 | 00/00/0000 |  |  |  |  | PASSED
TC107 | 00/00/0000 |  |  |  |  | PASSED
TC108 | 00/00/0000 |  |  |  |  | PASSED
TC109 | 00/00/0000 |  |  |  |  | PASSED
TC110 | 00/00/0000 |  |  |  |  | PASSED
TC111 | 00/00/0000 |  |  |  |  | PASSED
TC112 | 00/00/0000 |  |  |  |  | PASSED
TC113 | 00/00/0000 |  |  |  |  | PASSED
TC114 | 00/00/0000 |  |  |  |  | PASSED
TC115 | 00/00/0000 |  |  |  |  | PASSED
TC116 | 00/00/0000 |  |  |  |  | PASSED
TC117 | 00/00/0000 |  |  |  |  | PASSED
TC118 | 00/00/0000 |  |  |  |  | PASSED
TC119 | 00/00/0000 |  |  |  |  | PASSED
TC120 | 00/00/0000 |  |  |  |  | PASSED
TC121 | 00/00/0000 |  |  |  |  | PASSED
TC122 | 00/00/0000 |  |  |  |  | PASSED
TC123 | 00/00/0000 |  |  |  |  | PASSED
TC124 | 00/00/0000 |  |  |  |  | PASSED
TC125 | 00/00/0000 |  |  |  |  | PASSED
TC126 | 00/00/0000 |  |  |  |  | PASSED
TC127 | 00/00/0000 |  |  |  |  | PASSED
TC128 | 00/00/0000 |  |  |  |  | PASSED
TC129 | 00/00/0000 |  |  |  |  | PASSED
TC130 | 00/00/0000 |  |  |  |  | PASSED
TC131 | 00/00/0000 |  |  |  |  | PASSED
TC132 | 00/00/0000 |  |  |  |  | PASSED
TC133 | 00/00/0000 |  |  |  |  | PASSED
TC134 | 00/00/0000 |  |  |  |  | PASSED
TC135 | 00/00/0000 |  |  |  |  | PASSED
TC136 | 00/00/0000 |  |  |  |  | PASSED
TC137 | 00/00/0000 |  |  |  |  | PASSED
TC138 | 00/00/0000 |  |  |  |  | PASSED
TC139 | 00/00/0000 |  |  |  |  | PASSED
TC140 | 00/00/0000 |  |  |  |  | PASSED
TC141 | 00/00/0000 |  |  |  |  | PASSED
TC142 | 00/00/0000 |  |  |  |  | PASSED
TC143 | 00/00/0000 |  |  |  |  | PASSED
TC144 | 00/00/0000 |  |  |  |  | PASSED
TC145 | 00/00/0000 |  |  |  |  | PASSED
TC146 | 00/00/0000 |  |  |  |  | PASSED
TC147 | 00/00/0000 |  |  |  |  | PASSED
TC148 | 00/00/0000 |  |  |  |  | PASSED
TC149 | 00/00/0000 |  |  |  |  | PASSED
TC150 | 00/00/0000 |  |  |  |  | PASSED
Defect
Density
Defect
Distribution
Test Execution Status

## Dropdown Keys (hidden)
DROPDOWN KEYS
EXECUTION STATUS | IMPACT SEVERITY | DEFECT SEVERITY | DEFECT STATUS | IMPLEMENTATION STATUS | TEST CASE STATUS | CRITICALITY
PASSED | N/A | Minor | Open | Planned | Not Started | Low
FAILED | Low | Major | In Progress | Implemented | In Progress | Medium
Blocked | Medium | Critical | Closed | Attempted | Complete | High
Not Executed | High |  |  |  | Needs Review
| Critical |  |  |  | Approved
Overdue
On Hold